## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Chatbot in nodejs
PROJECT ID
PROJECT MANAGER | Jayanth GS
DOCUMENT VERSION
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Create Nodejs Server for Website |  | 2020-07-09 |  |  | localserver for website is developed | COMPLETED | REVIEWED
2 | Create Landing page for website |  | 2020-07-12 |  |  | landing page is developed | COMPLETED | REVIEWED
3 | create bot frame |  | 2020-07-18 |  |  | framework for bot is developed | COMPLETED | REVIEWED
4 | Enter Triggers And Responses in chatbot |  | 2020-07-22 |  |  | triggers with corresponding response set are matched in main js file of chatbot. | COMPLETED | REVIEWED
5 | Final Protoype |  | 2020-07-25 |  |  | Final prototype of project is developed. | COMPLETED | REVIEWED