## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Job Cloud
PROJECT MANAGER | Jayanth G S |  | EXECUTION PHASE START DATE: |  | 2020-06-15
PROJECT DELIVERABLE | Job Cloud Job Portal |  | EXECUTION PHASE END DATE: |  | 2020-07-31
PROJECT SCOPE | The Aim Is to Build Chatbot
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
Design
| SRS Document |  | 2020-06-23 | 2020-06-25 | 2 | COMPLETED
| Project Charter |  | 2020-06-25 | 2020-06-29 | 4 | COMPLETED
| Update Raid Log |  | 2020-07-05 | 2020-07-26 | 20 | COMPLETED
| Finalize Design |  | 2020-07-05 | 2020-07-09 | 2 | COMPLETED
Build
| Creating Landing |  | 2020-07-09 | 2020-07-11 | 3 | COMPLETED
| Creating Landing Page |  | 2020-07-12 | 2020-07-17 | 5 | COMPLETED
| create bot frame |  | 2020-07-18 | 2020-07-22 | 4 | COMPLETED
| Enter Triggers And Responses in chatbot |  | 2020-07-22 | 2020-07-24 | 2 | COMPLETED
| Final Protoype |  | 2020-07-25 | 2020-07-26 | 1 | COMPLETED