## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 0 | 1 | 0 | 0 | 0
| Project title: | Chatbot in Nodejs |  | Project Id: |  | Project Manager: | Jayanth GS |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: |  | Project Team Lead: |  |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 2 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Problem in Nodejs Server | Webpage Will Not Work Properly | Create Proper Server | Project Manager | High |  | Open | Risk
2 | Assumption | User Wrong Input Corresponding To no. of Queries | Might get different Response from Chatbot. | Conducting test Time to Time. | Project Manager |  |  | Open | Assumption
3 | [8 empty] | Issue
4 | [8 empty] | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24